## 18-10-2025
| Good | Need Improvements | Ideas | Kudos
Ebrar Sude Doğan | The team made clear progress from brainstorming to finalized project topics. | Team meetings can be more goal-oriented to save time. | Prepare meeting agendas beforehand. | All team.
Erdem Baran | All members contributed actively and shared creative project ideas. | Tasks are divided properly, but document reviews are not done regularly. | Schedule short review meetings or asynchronous review slots. | All team.
Kayrahan Toprak Tosun | Research responsibilities were distributed efficiently among members. | Research results can be summarized visually for better clarity. | Summarize findings visually or in a standardized format. | All team.
Tuna Kodal | Everyone completed their responsibilities on time and with minimal issues. A strong communication led to a successful sprint. | Ideas can be documented and organized more effectively. | An appropriate filing system can be established to record and maintain noteworthy ideas in written form. | All team.
| Ideas | Action items | Responsible
| Ideas can be documented and organized more effectively. | Basic hierarchical folder system creation. | Tuna Kodal
| Summarize findings visually or in a standardized format. | Use short summary slides or tables in the next sprint’s discussions. | Erdem Baran
| Schedule short review meetings or asynchronous review slots. | Set a 15-minute weekly review session to ensure everyone gives and receives feedback. | Ebrar Sude Doğan
| Prepare meeting agendas beforehand. | The Scrum Master drafts and shares an agenda before each meeting. | Kayrahan Toprak Tosun