## Sheet1
REQUIREMENTS TRACEABILITY MATRIX
Project Name | GUIDE
Project Type | Web-based travel planning software
Project Start Date | 04.10.2025
Project End Date | 15.12.2025
Project Sponsor | TOBB ETU - Department of Computer Science
Primary Driver | Individual travelers needing personalized travel plans
Secondary Driver | BIL495-496 Requirements and academic evaluation
Division | Faculty of Engineering / Department of Science
Project Manager/Department | Ebrar Sude Doğan / Department of Computer Science
ID | Associated ID | Technical Assumptions | Functional Requirement | Status | Architectural/Design Document | Technical Specification | System Components | Software Modules | Test Case Number | Tested In | Implemented In | Verification | Additional Comments
FR-H01 | To collect user preferences and constraints | The system shall allow the user to provide inputs for route generation. | IEEE_SDD_v1 – 3.3 Frontend UI; 3.2 Routing & Personalization Engine | Planned | IEEE_SRS_v2 – FR-H01 | Frontend UI; Routing & Personalization Engine | TripSetupForm; RouteRequestHandler API | FT-01 | Functional Test | TBD | Functional Testing | ISO/IEC/IEEE 29148:2018
FR-H02 | To generate personalized routes | The system shall generate an AI-based route plan according to the user’s preferences and time constraints. | IEEE_SDD_v1 – 3.2 Routing & Personalization Engine; 3.4 OSRM Integration | Planned | IEEE_SRS_v2 – FR-H02 | Routing & Personalization Engine; OSRM Service | RoutePlannerService; OSRMAdapter | IT-01 | Integration Test | TBD | Integration Testing | ISO/IEC/IEEE 29148:2018
FR-H03 | To provide user flexibility | The system shall allow the user to modify suggested destinations. | IEEE_SDD_v1 – 3.3 Itinerary Editor UI; 3.2 Routing Engine | Planned | IEEE_SRS_v2 – FR-H03 | Frontend UI; Routing & Personalization Engine | ItineraryEditor UI; RouteUpdater | FT-02 | Functional Test | TBD | Functional Testing | ISO/IEC/IEEE 29148:2018
FR-H04 | To deliver informative content | The system shall display descriptive information for each destination. | IEEE_SDD_v1 – 3.3 POI Details UI; 3.5 POI Repository | Planned | IEEE_SRS_v2 – FR-H04 | Frontend UI; POI Repository | POIDetailsPage; POIContentService | UI-01 | UI / System Test | TBD | UI Testing | ISO/IEC 25010:2011 (Usability)
FR-H05 | To provide multilingual accessibility | The system shall support text-to-speech (TTS) functionality for destination descriptions. | IEEE_SDD_v1 – 3.4 TTS & Multimedia Services; 3.3 Frontend UI | Planned | IEEE_SRS_v2 – FR-H05 | TTS Service; Frontend UI | TTSSynthesisAdapter; AudioPlayer | AV-01 | Audio / Usability Test | TBD | Audio Verification Testing | ISO/IEC 25010:2011 (Accessibility)
FR-H06 | To visualize planned routes | The system shall allow the user to view the generated route on a map. | IEEE_SDD_v1 – 3.3 Map Visualization Component; 3.2 Routing Engine | Planned | IEEE_SRS_v2 – FR-H06 | Map Visualization Component; Routing Engine | MapView; RouteGeometryAPI | UI-02 | UI / System Test | TBD | UI Testing | ISO/IEC 25010:2011 (Usability)
FR-H07 | To support time-aware scheduling | The system shall estimate the average visiting duration for each stop, use these estimations when planning time-limited trips, and display them to the user. | IEEE_SDD_v1 – 3.2 Routing & Personalization Engine | Planned | IEEE_SRS_v2 – FR-H07 | Routing & Personalization Engine | TimeAwareScheduler; ItineraryView | FT-03 | Functional Test | TBD | Functional Testing | ISO/IEC/IEEE 29148:2018
FR-L01 | To collect user preferences and constraints | The system shall allow the user to specify city/region, trip duration, distance limit, category filters, and places to exclude. | IEEE_SDD_v1 – 3.3 Frontend UI; 3.2 Routing Engine | Planned | IEEE_SRS_v2 – FR-L01 | Frontend UI; Routing Engine | TripFilterForm; RouteRequestHandler API | FT-04 | Functional Test | TBD | Functional Testing | ISO/IEC/IEEE 29148:2018
FR-L02 | To generate personalized routes | The system shall organize the generated route on a day-by-day basis and optimize it based on user inputs. | IEEE_SDD_v1 – 3.2 Routing & Personalization Engine | Planned | IEEE_SRS_v2 – FR-L02 | Routing & Personalization Engine | DailyItineraryBuilder | IT-02 | Integration Test | TBD | Integration Testing | ISO/IEC/IEEE 29148:2018
FR-L03 | To provide user flexibility | The system shall let the user remove unwanted stops, after which the system shall automatically regenerate an optimized route. | IEEE_SDD_v1 – 3.3 Itinerary Editor UI; 3.2 Routing Engine | Planned | IEEE_SRS_v2 – FR-L03 | Frontend UI; Routing Engine | ItineraryEditor UI; RouteReoptimizer | FT-05 | Functional Test | TBD | Functional Testing | ISO/IEC/IEEE 29148:2018
FR-L04 | To deliver informative content | The system shall display text descriptions, images, and map locations for each destination. | IEEE_SDD_v1 – 3.3 POI Details UI; 3.5 POI Repository | Planned | IEEE_SRS_v2 – FR-L04 | Frontend UI; POI Repository; Map Component | POIDetailsPage; MapMarkerRenderer | UI-03 | UI / System Test | TBD | UI Testing | ISO/IEC 25010:2011 (Usability)
FR-L05 | To provide multilingual accessibility | The system shall provide TTS in Turkish, English, and German for each destination description. | IEEE_SDD_v1 – 3.4 TTS & Multimedia Services; 3.3 Frontend UI | Planned | IEEE_SRS_v2 – FR-L05 | TTS Service; Frontend UI | TTSSynthesisAdapter; LanguageSelector | AV-02 | Audio / Usability Test | TBD | Audio Verification Testing | ISO/IEC 25010:2011
FR-L06 | To collect user preferences and constraints | The system shall validate user input for route generation and provide error messages. | IEEE_SDD_v1 – 3.3 Frontend UI; 3.2 Routing Engine | Planned | IEEE_SRS_v2 – FR-L06 | Frontend UI; Routing Engine | InputValidator; ErrorMessageHandler | FT-06 | Functional Test | TBD | Functional Testing | ISO/IEC/IEEE 29148:2018
FR-L07 | To visualize planned routes | The system shall allow the user to zoom, pan, and interact with the route map. | IEEE_SDD_v1 – 3.3 Map Visualization Component | Planned | IEEE_SRS_v2 – FR-L07 | Map Visualization Component; Frontend UI | MapView; MapInteractionController | UI-04 | UI / System Test | TBD | UI Testing | ISO/IEC 25010:2011 (Usability)
EIR-H01 | To ensure web accessibility | The system shall operate via a web-based user interface. | IEEE_SDD_v1 – 3.3 Frontend UI | Planned | IEEE_SRS_v2 – EIR-L01 | Frontend UI | WebFrontendShell | US-01 | Usability Test | TBD | Usability Testing | WCAG 2.1
EIR-H02 | To ensure web accessibility | The system shall support access from both desktop and mobile browsers. | IEEE_SDD_v1 – 3.3 Frontend UI | Planned | IEEE_SRS_v2 – EIR-L02 | Frontend UI | ResponsiveLayoutManager | US-02 | Usability Test | TBD | Usability Testing | WCAG 2.1
EIR-H03 | To ensure web accessibility | The system shall support access from different screen sizes. | IEEE_SDD_v1 – 3.3 Frontend UI | Planned | IEEE_SRS_v2 – EIR-L03 | Frontend UI | ResponsiveLayoutManager | US-03 | Usability Test | TBD | Usability Testing | ISO/IEC 25010:2011 (Usability)
EIR-H04 | To ensure accessible interaction for diverse users | The system shall comply with WCAG 2.1 Level AA accessibility guidelines for core user flows (route creation, itinerary editing, POI details). | IEEE_SDD_v1 – 3.3 Frontend UI | Planned | IEEE_SRS_v2 – EIR-H04 | Frontend UI | WebFrontendShell; CoreUserFlowPages | AX-01 | Accessibility / Usability Test | TBD | Usability / Accessibility Testing | WCAG 2.1; ISO/IEC 25010:2011 (Usability, Accessibility)
PR-H01 | To guarantee acceptable performance | The system shall generate and display a complete route suggestion within an average of 5 seconds after receiving the user’s request. | IEEE_SDD_v1 – 3.2 Routing Engine; 4.2 Performance Considerations | Planned | IEEE_SRS_v2 – PR-H01 | Routing Engine; Backend Infrastructure | RoutePlannerService; PerformanceMonitor | PT-01 | Performance Test | TBD | Performance Testing | ISO/IEC 25010:2011 (Performance Efficiency)
PR-H02 | To ensure scalability | The system shall support at least 1000 concurrent users. | IEEE_SDD_v1 – 3.2 Routing Engine; Backend Infrastructure | Planned | IEEE_SRS_v2 – PR-H02 | Backend Infrastructure; OSRM Service | ScalingConfig; LoadTestScripts | LT-01 | Load Test | TBD | Load Testing | ISO/IEC 25010:2011 (Performance – Capacity)