## 5-11-2025
| Good | Need Improvements | Ideas | Kudos
Ebrar Sude Doğan | The team maintained consistent progress despite the sprint containing mostly documentation-heavy tasks. | Consistency checks across diagrams and text could be more structured. | Add a lightweight consistency checklist for diagrams and text sections. | All team.
Erdem Baran | Cross-checking between documents improved overall consistency and reduced ambiguity. | Earlier clarification of requirements could further reduce last-minute adjustments. | Define criteria at sprint kickoff to avoid ambiguity later in the sprint. | All team.
Kayrahan Toprak Tosun | Task ownership was well-distributed, preventing bottlenecks around specific members. | Review cycles happened slightly later than ideal, compressing feedback time. | Schedule mid-sprint micro-reviews to spread out feedback cycles. | All team.
Tuna Kodal | Quality artifacts (QMP, Quality Model, checklists) were collaboratively refined with minimal rework. | Documentation workload planning can be more granular to avoid uneven effort spikes. | Break large documentation tasks into smaller sub-tasks with internal mini-deadlines. | All team.
| Ideas | Action items | Responsible
| Add a lightweight consistency checklist for diagrams and text sections. | Create and share a one-page consistency checklist and require each member to run it before submitting any document or diagram. | Ebrar Sude Doğan
| Define criteria at sprint kickoff to avoid ambiguity later in the sprint. | Prepare a short “Expectations & Criteria” sheet and review it together during sprint planning. | Erdem Baran
| Schedule mid-sprint micro-reviews to spread out feedback cycles. | Add a fixed 10-minute mid-sprint review slot to the team calendar for quick alignment and early corrections. | Kayrahan Toprak Tosun
| Break large documentation tasks into smaller sub-tasks with internal mini-deadlines. | Split each major documentation item into 2–3 sub-tasks on the sprint board and assign internal due dates to evenly distribute workload. | Tuna Kodal