## 5-11-2025
| Good | Need Improvements | Ideas | Kudos
Ebrar Sude Doğan | Team members adapted quickly to the shifting documentation focus, maintaining overall sprint momentum. | Some sections were started late, leaving limited time for polishing and peer review. | Break large documentation tasks into smaller, time-boxed sub-tasks. | All team.
Erdem Baran | Review meetings were concise and productive, helping finalize drafts without unnecessary discussion loops. | Mid-sprint coordination could be slightly stronger. | Introduce a lightweight mid-sprint sync. | All team.
Kayrahan Toprak Tosun | Communication through the shared workspace improved, making it easier to track contributions. | Some responsibilities were not fully defined at the start of the sprint. | Clarify ownership before sprint kickoff. | All team.
Tuna Kodal | Review cycles were efficient, with team members providing timely feedback to finalize documentation. | More frequent short check-ins might help maintain alignment. | Use micro-updates to maintain visibility. | All team.
| Ideas | Action items | Responsible
| Break large documentation tasks into smaller, time-boxed sub-tasks. | Add internal mini-deadlines to the sprint board so each section progresses earlier in the sprint. | Ebrar Sude Doğan
| Introduce a lightweight mid-sprint sync. | Schedule a 10-minute mid-sprint alignment check each sprint to monitor progress and unblock issues. | Kayrahan Toprak Tosun
| Clarify ownership before sprint kickoff. | During sprint planning, assign clear owners for each document section and record them in the shared workspace. | Erdem Baran
| Use micro-updates to maintain visibility. | Require each team member to post a brief daily update (1–2 sentences) in the shared channel (WhatsApp) to improve transparency. | Tuna Kodal