## 5-11-2025
| Good | Need Improvements | Ideas | Kudos
Ebrar Sude Doğan | Everyone completed their individual tasks on time. | The current task distribution process was not detailed enough. | Conduct a more comprehensive pre-sprint planning review to clarify and balance task assignments. | All team.
Erdem Baran | No communication breakdowns occurred; effective communication was established quickly whenever needed. | Important discussions and decisions were sometimes left undocumented, leading to minor confusion later on. | Assign a rotating note-taker to document all key discussions, decisions, and updates in a shared space. | All team.
Kayrahan Toprak Tosun | Meetings were highly effective and goal-oriented. | Idea-sharing during the sprint was limited, and team-wide brainstorming could have been more frequent. | Schedule mid-sprint brainstorming sessions to encourage continuous feedback and creative input. | All team.
Tuna Kodal | After completing their tasks, team members reviewed and provided feedback on each other’s work instead of limiting themselves to their own responsibilities. | Changes occurring during the sprint were not tracked consistently. | Assign a team member responsible for observing and recording sprint changes, ensuring that all updates are noted and communicated clearly. | All team.
| Ideas | Action items | Responsible
| Conduct a more comprehensive pre-sprint planning review to clarify and balance task assignments. | Hold a 15-minute mini planning meeting before Sprint 3 to finalize detailed task distribution. | Ebrar Sude Doğan
| Assign a rotating note-taker to document all key discussions, decisions, and updates in a shared space. | Create a “general notes” folder in the shared drive; assign note-takers in rotation. | Tuna Kodal
| Schedule mid-sprint brainstorming sessions to encourage continuous feedback and creative input. | Add a mid-sprint meeting to the calendar for collaborative review and discussion. | Kayrahan Toprak Tosun
| Assign a team member responsible for observing and recording sprint changes, ensuring that all updates are noted and communicated clearly. | Designate a “change tracker” role each sprint — this person will document key updates, decisions, and adjustments, then present a brief summary. | Erdem Baran