TOBB ETU

Economy & Technology University

BIL 495 / YAP 495

Project Management Plan (PMP)

Version 2.0

Reference: IEEE 1058 / ISO/IEC 12207

Table of Contents

- Project Overview

- Organization and Roles

- Project Schedule

- Budget and Resources

- Risk Management

- Quality Assurance

- Appendix

- References

1. Project Overview

1.1. Project Goals

- The GUIDE (Guided User Itinerary & Destination Explorer) project aims to develop an intelligent, context-aware travel guidance system. The primary goals are:

| Goal Category | Description |
| --- | --- |
| Enhanced Experience | Provide enhanced traveler experience and engagement by offering a unified platform that replaces multiple fragmented travel tools |
| Personalized Planning | Develop a personalized route planning system that considers user preferences, time constraints, and travel modes |
| POI Identification | Identify and recommend points of interest (POIs) based on user-defined themes such as cultural, historical, culinary, or scenic tours |
| Multilingual Support | Deliver contextual and multilingual information through text and text-to-speech (TTS) features in Turkish, English, and German |
| User Interface | Design an interactive and user-friendly interface that facilitates user-application interaction |
| Modularity | Ensure modularity and scalability for future integration of enhanced features |

1.2. Project Deliverables

The GUIDE project will produce the following key deliverables:

Technical Deliverables:

| Deliverable | Description |
| --- | --- |
| Web Application | A fully functional web-based application with responsive design |
| Backend System | Backend system with RESTful API architecture |
| Database | Database containing pre-fetched POI information, routes, and user preference data |
| AI Algorithm | AI-driven route generation and POI ranking algorithm |
| TTS Module | Integrated text-to-speech (TTS) module supporting three languages |
| Map Interface | Map visualization and navigation interface powered by OpenStreetMap and OSRM |

Documentation Deliverables:

| Document Type | Standard/Version |
| --- | --- |
| Project Management Plan (PMP) | IEEE 1058 v2 |
| Software Requirements Specification (SRS) | IEEE 830 v2 |
| Software Architecture Document (SAD) | ISO/IEC/IEEE 42010 v1 |
| Software Design Description (SDD) | IEEE 1016 v1 |
| Software Test Plan (STP) | IEEE 829 v1 |
| Quality Management Plan (QMP) | ISO/IEC 25010 v1 |
| Technology Comparison Report | - |
| Sprint Review Reports | Sprints 1-5 |
| UML Diagrams | Complete set |
| Traceability Matrix | Requirements-Design-Test |
| Test Coverage & Defect Density | Calculations |
| Gantt Chart | v2 |
| Control Checklists | SRS/SDD/STP/Tech |

Presentation Deliverables:

- Sprint review presentations (5 completed)

- Final project demonstration

1.3. Stakeholders

Primary Stakeholders:

Development Team (QUAD-CORE):

| Name | Role |
| --- | --- |
| Ebrar Sude Doğan | Project Manager |
| Erdem Baran | Backend Leader & Documentation Coordinator |
| Kayrahan Toprak Tosun | Scrum Master & API Integration Specialist |
| Tuna Kodal | Frontend Leader & Repository Manager |

Academic Supervisors:

- Course instructors from TOBB ETÜ BIL 495/YAP 495

- Project advisors

End Users:

- Individual travelers seeking personalized travel experiences

- Tourists visiting Türkiye

Secondary Stakeholders:

- Data and Service Providers: UNESCO, OpenStreetMap, Wikipedia, Flickr, Pixabay, ElevenLabs

- Institutional: TOBB University, potential tourism sector partners

- Compliance: KVKK/GDPR authorities

1.4. Project Scope Summary

Route Planning Service: User preference input, AI-driven POI ranking, optimized route generation, interactive map interface

Guidance Service: Textual POI descriptions, multilingual audio guidance, visual content

Technical Implementation: Web-based platform, RESTful API, responsive UI, external API integrations

Exclusions: Real-time traffic/weather, social media connectivity, dynamic route adjustments, mobile native apps, multi-user planning

1.5. Success Criteria

- Functional web application deployed and accessible

- Personalized routes based on user preferences

- TTS functionality in Turkish, English, German

- Positive user acceptance feedback

- Complete documentation package

- All BIL 495 requirements fulfilled

- System demonstrable with no critical bugs

2. Organization and Roles

The GUIDE project is developed by four team members with Ebrar Sude Doğan as Project Manager and Kayrahan Toprak Tosun as Scrum Master.

Throughout Sprints 1-5, the team maintained consistent responsibilities with balanced workload distribution across design, implementation, testing, and documentation.

Core Responsibilities:

| Team Member | Responsibilities |
| --- | --- |
| Ebrar Sude Doğan | Project Management, UI/UX Design, Frontend Architecture, SRS/SAD preparation |
| Erdem Baran | Backend Development, Database Design, Documentation Coordination, Activity/State Machine Diagrams |
| Kayrahan Toprak Tosun | Sprint Tracking, API Integration, Routing Algorithms, Data Flow Diagram, Test Document |
| Tuna Kodal | Frontend Development, Repository Management, Use Case/Component/Sequence Diagrams, Traceability |

3. Project Schedule

The project executed five documentation and design sprints (Oct 2024 - Dec 2025), with implementation planned for 2026.

3.1 Completed Sprints

Sprint 1 (Sep 29 - Oct 13, 2025): Topic Selection & Research

Focus: Project brainstorming, topic selection (GUIDE and SHELF), feasibility research

Key Deliverables:

- Topic proposals for GUIDE and SHELF projects

- Dataset research (UNESCO, OpenStreetMap, tourism data)

- API identification (OSM, OSRM, Wikipedia, ElevenLabs)

- Problem definition, scope, user profiles

Status: COMPLETED - All tasks finished, strong collaboration

Sprint 2 (Oct 18-30, 2025): Requirements & Initial Documentation

Focus: SRS preparation, PMP creation, initial diagrams

Key Deliverables:

- Software Requirements Specification (SRS) v1 - IEEE 830

- Project Management Plan (PMP) v1 - IEEE 1058

- Use Case Diagram (Tuna Kodal)

- Activity Diagram (Erdem Baran)

- Context Diagram

- Initial Gantt Chart (Kayrahan Toprak Tosun)

- System architecture definition

Status: COMPLETED - Documentation framework established

Sprint 3 (Nov 7-19, 2025): Architecture & Detailed Design

Focus: System architecture, detailed requirements, design documentation

Key Deliverables:

- Technology Comparison Report (Ebrar Sude Doğan)

- SRS v2 with 10 refined requirements (Erdem Baran)

- Software Architecture Document (SAD) v1

- Software Design Description (SDD) v1

- Data Flow Diagram (Kayrahan Toprak Tosun)

- Class Diagram (Erdem Baran)

- Component Diagram (Tuna Kodal)

- Requirements-Design Traceability (Ebrar Sude Doğan)

- 2 Integration Test Scenarios (Kayrahan Toprak Tosun)

- Control Lists initial draft (Tuna Kodal)

Challenges: Workload imbalance due to exam schedules, MÜDEK compliance revisions required

Status: COMPLETED - Architecture and design foundation established

Sprint 4 (Nov 20 - Dec 3, 2025): Testing Framework & Behavioral Modeling

Focus: Test planning, behavioral diagrams, quality metrics

Key Deliverables:

- Software Test Plan (STP) v1 - IEEE 829 (Erdem Baran, Kayrahan Toprak Tosun)

- Sequence Diagram (Tuna Kodal) - Most challenging due to workflow complexity

- State Machine Diagram (Erdem Baran)

- Deployment Diagram (Ebrar Sude Doğan)

- Complete Requirements-Design-Test Traceability (Tuna Kodal)

- Test Coverage Calculation (Kayrahan Toprak Tosun)

- Defect Density Calculation (Erdem Baran)

- Gantt Chart v2 (Kayrahan Toprak Tosun)

- Design Document Revision (Ebrar Sude Doğan)

Status: COMPLETED - Testing framework established, all deliverables on time

Sprint 5 (Dec 4-12, 2025): Quality Assurance & Final Documentation

Focus: Quality management, metrics definition, final consolidation

Key Deliverables:

- Quality Management Plan (QMP) v1 - ISO/IEC 25010 (Tuna Kodal)

- ISO/IEC 25010 Quality Model Definition (Kayrahan Toprak Tosun)

- Quality Metrics Measurement and Results (Ebrar Sude Doğan)

- Final System Architecture Diagram (Tuna Kodal)

- Finalized Control Checklists (SRS/SDD/STP/Tech) (Kayrahan Toprak Tosun)

- PMP v2 (This document) (Erdem Baran)

- Final Deliverables Package (Ebrar Sude Doğan)

Challenges: QMP complexity, final exam period workload

Status: COMPLETED - All quality documentation finalized

3.2 Planned Phases

- Implementation Phase (Jan-Feb 2026): Backend and frontend development

- Testing & Optimization (Mar-Apr 2026): System testing, bug fixes, performance tuning

- Final Demonstration (Apr 2026): Project presentation and delivery

3.3 Project Timeline Summary

Sep 29, 2025: Project kickoff

Oct-Nov 2025: Requirements and architecture definition (Sprints 1-3)

Nov-Dec 2025: Design, testing, and quality framework (Sprints 4-5)

Dec 12, 2025: Documentation phase complete

Jan-Apr 2026: Implementation and testing phases (planned)

4. Budget and Resources

4.1 Human Resources

Four-member team with specialized roles maintained throughout Sprints 1-5

4.2 Technical Resources

- Mapping: OpenStreetMap, OSRM

- Database: PostgreSQL with PostGIS

- Development: VS Code, GitHub, Node.js, React

- TTS: ElevenLabs

- Documentation: Google Drive, Lucidchart, Draw.io

4.3 Financial Overview

Minimal costs leveraging open-source tools:

- Hosting: ~$10-15/month

- APIs: ~$5-10/month

- Miscellaneous: ~$30 reserve

5. Risk Management

Key risks monitored throughout Sprints 1-5:

- API Compatibility: Modular integration, local data storage

- API Key Expiration: Regular monitoring, backup credentials

- Environment Inconsistencies: Cross-browser testing validated

- TTS Quality: Team language verification (Turkish, English, German)

- Map Data Accuracy: User communication about static data

- Data Freshness: Periodic verification

- Mobile Performance: Responsive design optimization

- Algorithm Accuracy: Refinement based on feedback

- Route Generation Errors: Validation mechanisms

- User Expectations: Clear capability communication

- Scalability: Backend designed for future scaling

- Time Dependencies: Buffer periods validated in practice (Sprints 3-5)

- Workload Imbalance: Task redistribution during Sprint 3 exam period

- Documentation Consistency: Peer review process established

- Cultural/Linguistic Issues: Team review validated

6. Quality Assurance

Quality governed by QMP v1 (Sprint 5) aligned with ISO/IEC 25010

6.1 Quality Model

ISO/IEC 25010 characteristics (defined Sprint 5):

- Functional Suitability, Performance Efficiency, Usability

- Reliability, Security, Maintainability, Portability

6.2 Quality Metrics (Sprint 4-5)

- Test Coverage: Calculated Sprint 4

- Defect Density: Methodology defined Sprint 4

- Requirements Traceability: Complete bidirectional (Sprint 4)

- Code Quality: Metrics defined Sprint 5

6.3 Quality Control Processes

- Sprint Reviews: 5 completed with retrospectives

- Peer Reviews: All documents team-reviewed

- Compliance Checklists: Finalized Sprint 5

- Testing Framework: Comprehensive (Sprint 4)

- Standards: IEEE/ISO/IEC compliance verified

6.4 Impact Considerations

Societal: Enhanced cultural understanding through travel

Economic: Minimal costs, scalable architecture

Legal/Ethical: GDPR/KVKK compliance, bias mitigation

7. Appendix

Appendix A: Acronyms

- GUIDE: Guided User Itinerary & Destination Explorer

- PMP: Project Management Plan

- SRS: Software Requirements Specification

- SAD: Software Architecture Document

- SDD: Software Design Description

- STP: Software Test Plan

- QMP: Quality Management Plan

- POI: Point of Interest

- TTS: Text-to-Speech

- OSRM: Open Source Routing Machine

Appendix B: Sprint Documents

- Sprint 1 Review (Sep 29 - Oct 13, 2025)

- Sprint 2 Review (Oct 18-30, 2025)

- Sprint 3 Review (Nov 7-19, 2025)

- Sprint 4 Review (Nov 20 - Dec 3, 2025)

- Sprint 5 Review (Dec 4-12, 2025)

- Sprint Retrospectives (5 completed)

- QUAD-CORE Gantt Chart v2

Appendix C: Technical Documents

- SRS v2 (10 refined requirements)

- SAD v1

- SDD v1

- STP v1

- QMP v1

- Technology Comparison Report

- Traceability Matrix (Requirements-Design-Test)

Appendix D: External APIs

- OpenStreetMap: Road network data

- OSRM: Route calculation

- Wikipedia API: POI descriptions

- Flickr/Pixabay: Images

- ElevenLabs: Multilingual TTS

Appendix E: Technology Stack

Frontend: HTML5, CSS3, JavaScript, React.js, Leaflet.js

Backend: Python/Node.js, RESTful API

Database: PostgreSQL with PostGIS

Tools: Git, GitHub, VS Code, Postman

8. References

- IEEE 1058-1998: Software Project Management Plans

- IEEE 830: Software Requirements Specification

- IEEE 1016: Software Design Description

- IEEE 829: Software Test Documentation

- ISO/IEC 12207: Software life cycle processes

- ISO/IEC 25010: Quality Requirements and Evaluation

- ISO/IEC/IEEE 42010: Architecture Description

- OpenStreetMap. https://www.openstreetmap.org

- OSRM. http://project-osrm.org

- ElevenLabs. https://elevenlabs.io

- UNESCO World Heritage. https://www.unesco.org.tr

- KVKK. https://www.kvkk.gov.tr

- GDPR (EU) 2016/679

- QUAD-CORE Team. (2024-2025). GUIDE Project Documentation