## Gantt Chart
| PROJECT TITLE | GUIDE (Guided User Itinerary & Destination Explorer) | [10 empty] | TEAM NAME |  |  |  | QUAD-CORE | [7 empty] | Version information is placed on next page
| PROJECT MANAGER | Ebrar Sude Doğan | [10 empty] | DATE |  |  |  | 24.11.2025
|  |  |  | PHASE ONE | [6 empty] | PHASE TWO | [20 empty] | PHASE THREE | [20 empty] | PHASE FOUR | [13 empty] | PHASE FIVE | [13 empty] | PHASE SIX
WBS NUMBER | TASK TITLE | TASK OWNER | PCT OF TASK COMPLETE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
|  |  |  | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
1 | System Initialization & Architecture Setup
1.1 | Repository and environment configuration | Tuna | 0% | bar: WEEK 1 M to WEEK 1 T
1.2 | API key registration & credential management | Kayrahan | 0% | bar: WEEK 1 T to WEEK 1 R
1.3 | Module interfaces | Ebrar | 0% | bar: WEEK 1 T to WEEK 1 F
1.4 | Database initialization | Erdem | 0% | bar: WEEK 1 T to WEEK 1 F
2 | Core Backend & Routing Logic
2.1 | Database schema for POIs, routes, user preferences | Erdem | 0% | bar: WEEK 1 U to WEEK 4 W
2.2 | Integration of OpenStreetMap and OSRM for route computation | Kayrahan | 0% | bar: WEEK 1 U to WEEK 4 F
2.3 | Implementation of ranking algorithm | Ebrar | 0% | bar: WEEK 1 U to WEEK 4 M
2.4 | RESTful API endpoints for route creation, POI retrieval, and language setup | Tuna | 0% | bar: WEEK 1 F to WEEK 3 W
3 | Frontend Design & UI Implementation
3.1 | Low-fidelity wireframes and navigation flow | Ebrar | 0% | bar: WEEK 4 T to WEEK 6 M
3.2 | Development of home, route planner, and POI detail pages | Tuna | 0% | bar: WEEK 3 U to WEEK 5 U
3.3 | Map visualization | Erdem | 0% | bar: WEEK 4 T to WEEK 6 W
3.4 | Responsive design testing | Kayrahan | 0% | bar: WEEK 4 F to WEEK 5 U; WEEK 6 S to WEEK 7 M
4 | External API & Multimedia Integration
4.1 | Wikipedia & UNESCO API integration for POI metadata | Kayrahan | 0% | bar: WEEK 7 R to WEEK 8 W
4.2 | Flickr & Pixabay API for image retrieval | Erdem | 0% | bar: WEEK 6 F to WEEK 8 M
4.3 | ElevenLabs TTS integration | Tuna | 0% | bar: WEEK 6 R to WEEK 8 S
4.4 | Backend–frontend synchronization for multilingual data | Ebrar | 0% | bar: WEEK 7 R to WEEK 8 R
5 | Testing, Evaluation & Optimization
5.1 | Unit and integration testing of backend modules | Ebrar | 0% | bar: WEEK 6 R to WEEK 7 T; WEEK 8 U to WEEK 10 R
5.2 | UI functionality testing | Tuna | 0% | bar: WEEK 9 T to WEEK 11 R
5.3 | Load testing and optimization | Erdem | 0% | bar: WEEK 8 R to WEEK 11 W
5.4 | Fixing edge cases: route calculation errors, API rate limits, TTS output accuracy | Kayrahan | 0% | bar: WEEK 8 U to WEEK 11 T
6 | Documentation & Buffer Period
6.1 | Report, manual, and deployment documentation | All team | 0% | bar: WEEK 11 F to WEEK 12 U
6.2 | Demo preparation and presentation design | All team | 0% | bar: WEEK 12 M to WEEK 12 F
6.3 | Buffer for overflow tasks or delayed modules | All team | 0%

## Version Information
V2 UPDATES
- Core Backend Development and Routing Logic Implementation durations were extended to reflect their higher architectural complexity and dependency load.
- Frontend Integration and Multimedia and External API & Multimedia Integration Integration phases were slightly reduced in duration, since their tasks are now clearer and more predictable based on the finalized design.
- Testing, Evaluation & Optimization phases were extended to allocate additional time for regression testing, debugging, scenario coverage, and multimedia verification.
- Phase timelines were updated to better match realistic team capacity and the expected turnaround times for API stabilization, multimedia processing, and routing service validation.
* No changes were made in Sprint 5 compared to Sprint 4; therefore, the version number has not been updated for this sprint.