## 5-11-2025
| Good | Need Improvements | Ideas | Kudos
Ebrar Sude Doğan | The team demonstrated strong consistency in maintaining document quality and completeness across multiple artifacts. | Dependencies between documents occasionally caused delays when upstream sections were not ready. | Define explicit dependency chains at the start of the sprint so each member knows when their work can begin or continue. | All team.
Erdem Baran | Review sessions were efficient and helped polish documents quickly, reducing unnecessary rework. | Some reviews came late in the sprint, limiting the time available for final refinements. | Introduce earlier review cycles to catch structural issues sooner and distribute refinement work more evenly. | All team.
Kayrahan Toprak Tosun | The team maintained steady progress on documentation-heavy tasks, ensuring that major deliverables were completed on time. | Workload balancing across members could be improved. | Introduce a workload visibility chart so distribution can be adjusted proactively throughout the sprint. | All team.
Tuna Kodal | Collaboration on complex diagrams (Sequence, State Machine, Deployment) was handled effectively, with clear division of responsibilities. | Diagram revisions sometimes required multiple iterations due to differing interpretations of system behavior. | Use a short pre-diagram conceptual walkthrough to align on the behavior flow before diagramming. | All team.
| Ideas | Action items | Responsible
| Define explicit dependency chains at the start of the sprint so each member knows when their work can begin or continue. | Create a shared “dependency map” at sprint planning and publish it in the workspace for all members to reference. | Ebrar Sude Doğan
| Introduce earlier review cycles to catch structural issues sooner and distribute refinement work more evenly. | Schedule a mid-sprint review checkpoint to validate document structure and address issues before final drafting. | Erdem Baran
| Introduce a workload visibility chart so distribution can be adjusted proactively throughout the sprint. | Prepare a simple workload overview board (task count or hours) and update it during stand-ups to rebalance tasks when needed. | Kayrahan Toprak Tosun
| Use a short pre-diagram conceptual walkthrough to align on the behavior flow before diagramming. | Organize a 10-minute pre-diagram session where the team agrees on the flow and responsibilities before any diagramming begins. | Tuna Kodal